## Start Here
The AMPERE Toolkit
Companion workbook to the AMPERE Protocol, Version 5.1 · Metro Power Corporation · September 2026
Status: Issued, Version 5.1, approved September 22, 2026. Free to use and adapt under Protocol Section 30.4.
How to use
• Each sheet names the Protocol section it implements. The Protocol holds the rules; this workbook holds the forms.
• Yellow cells with blue text are for data entry. Other cells hold labels or formulas and should not be overwritten.
• Rows marked EXAMPLE show the expected format; delete or overwrite them.
• Default targets and thresholds are provisional Metro Power recommendations, not regulatory or service standards. Confirm them in approved plans; ERC standards prevail when issued.
• Lean core (smaller utilities): A1, A2, M2, M3, P1, P2, P5, P6, P7, W1 Gate Log, W1 Tailoring & Deviations, W2 Cyber & Privacy, W3 Complaint Log, R Rollout Cohorts; plus K2 Sector Submission under a sector framework.
• Free to use and adapt under Protocol Section 30.4; provided without warranty.
• Save a copy per utility and program. Record the Protocol and Toolkit versions used.
Sheet | Stage / workstream | Purpose | Protocol reference | Lean core
A1 Readiness Scoring | A: Assess | Readiness scores, knockouts, Gate 1/2/4 readiness checks; optional maturity survey | Section 6; Annex A | Yes
A2 Baseline KPIs | A: Assess | Operational baseline, same definitions as pilot KPIs | Sections 6, 21; Annex D | Yes
A4 Workforce Matrix | A / M; W1 | Capability gaps, training, role changes | Section 12
M1 Comms Scoring | M: Model | Weighted comparison of communication options | Section 15.4
M2 Business Case | M / E1 | Component-life replacements, costs, ramped benefits, NPV, IRR, payback, sensitivity, delay scenario, options, rate indicator | Sections 19, 20.3 | Yes
M3 Assumptions | M / E1 | Source type and range for every assumption | Section 19.1 | Yes
M4 Benefit Mapping | M / E1 | Asset → function → benefit → beneficiary; counted test; non-monetary effects | Sections 19.3–19.4
M5 Requirements Compliance | M / P | Bidder compliance against Annex E requirements | Annex E
P1 Pilot KPI Tracker | M / P | Hypotheses, thresholds, margins, per-stratum results and pass rule | Sections 8.6, 21.1; Annex C | Yes
P2 Site & Sampling | M: Model | Site selection, sample-size calculator with finite-population correction, census strata | Section 8.6 | Yes
P3 Pilot Budget | M / P | Budget, commitments, actuals | Sections 7–8
P4 Program Plan | A–E1 | Activities, owners, dates, deliverables, reviews, gates | Sections 5–9
P5 Acceptance Tests | P: Pilot | Test catalog (TC-###) | Section 8; Annex E | Yes
P6 Defect Log | P / R / E2 | Functional defects; security findings with remediation deadlines; Gate 3–5 checks | Sections 8, 16.1 | Yes
P7 Analysis & Amendments | M / P / E | Analysis plan and dated amendment log | Section 8.6; Annex C | Yes
W1 Risk Register | All; W1 | Program risks (RK-##) with scoring | Sections 5, 12
W1 Gate Log | All; W1 | Every gate decision, conditions, independent review rating | Sections 5.1, 5.4; Annex B | Yes
W1 Tailoring & Deviations | All; W1 | Tailoring and deviation approvals; mandatory-set check | Section 2.5 | Yes
W1 Document Register | All; W1 | Deliverables, versions, approvers, status | Section 5.1
W1 Change Log | R; W1 | Changes after Gate 4 and approval level | Section 10.7
W1 Stakeholder Plan | All; W1/W3 | Stakeholder communication, including barangays and LGUs | Sections 12, 14.1, 17
W2 Cyber & Privacy | All; W2 | Controls with CSF 2.0 function, current/target state, program Tier | Section 16 | Yes
W3 Complaint Log | P / R / E2; W3 | Complaints, service levels, escalation, meter-test turnaround | Section 17.5 | Yes
W3 Consumer Education | M / P / R; W3 | Education materials and activities | Section 17
K Reporting Cadence | P / R / E2 | Reports, frequency, audience, owners | Section 21.4
K2 Sector Submission | When a sector framework applies | Quarterly submission to an Adopting Body (Annex H dataset) | Section 26; Annex H | Sector
R Rollout Cohorts | R: Roll Out | Cohort checks, installation quality, pause triggers | Sections 10.6, 10.9 | Yes
R Meter Logistics | P / R | Lot receiving inspection; stock reconciliation | Section 10.10
R Benefits Tracker | R / E2 | Benefits realized vs business case (quarterly) | Sections 10, 19.3
E2 Failure Tracking | R / E2 | Failure rates by model/batch/firmware; warranty | Section 20.3
Regulatory Register | All | Instruments to confirm and monitor | Section 14
This Toolkit is practitioner guidance from Metro Power Corporation. It is not a regulatory issuance and does not replace legal, regulatory, or engineering judgment.

## A1 Readiness Scoring
A1: Readiness Assessment Scoring
Stage A · Protocol Section 6 and Annex A. Score each category 1–4 with evidence. Gate results calculate automatically; averages are for information only.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Category | Score (1–4) | Evidence (documents, data, observed practice) | Key gap | Closure action | Owner | Due date | 1: Initial | 2: Developing | 3: Pilot-ready | 4: Scale-ready
Governance | [6 empty] | No sponsor or structure | Sponsor named; structure informal | Steering Committee and TWG chartered; decision rights documented | Proven program governance on comparable projects
Organization and workforce | [6 empty] | No AMI skills or plan | Some skills; training needs known | Core team assigned; training plan funded | Trained staff across operations, IT, billing, and field
Technology and systems | [6 empty] | Legacy systems; no export capability | Systems documented; integration uncertain | CIS exchanges data through defined interfaces; test environments available | Integrated enterprise systems with proven interfaces
Communications | [6 empty] | No coverage information | Desk-based coverage information | Field survey completed for pilot areas | Surveyed architecture for full service area
Cybersecurity and privacy | [6 empty] | No policy; no DPO | Policy drafted; DPO designated | Minimum controls (Protocol 16.1) planned and resourced; PIA started | Controls operating and independently tested
Operations and billing (VEE) | [6 empty] | Manual processes; no exception handling | Procedures partly documented | VEE rules and billing exception process defined for pilot | VEE operating with audit and reconciliation
Consumer engagement | [6 empty] | No plan or channels | Channels exist; no AMI plan | Pilot engagement plan and complaint process ready | Proven engagement and complaint analytics
Data and baseline | [6 empty] | Records unreliable; baseline not measurable | Baseline partly measurable | Baseline KPIs measured; mapping verified in pilot areas | Baseline and mapping verified across service area
Knockout items (Protocol Annex A.2)
Condition | Met? (Y/N) | Evidence
Executive sponsor with authority over the departments involved is named
Data Protection Officer is designated
Customer, meter, and billing data can be extracted from the CIS
Management has committed to measuring the operational baseline
Budget authority for Stage M is confirmed
Gate results
Check | Result | Rule
Categories scored | 0 of 8 | All eight must be scored
Lowest category score |  | Used for gate rules
Knockout items cleared | Incomplete | All five conditions must be Y
Gate 1: Proceed to Model | INCOMPLETE | No knockouts; every category ≥ 2
Gate 2: Pilot approval (readiness part) | INCOMPLETE | Governance, cybersecurity & privacy, operations & billing, consumer engagement, data & baseline ≥ 3; others ≥ 2
Gate 4: Investment decision (readiness part) | INCOMPLETE | Every category ≥ 3 (re-score before Gate 4)
Average score (information only) |  | Never used to pass a gate
Optional: smart grid maturity survey (planning aid, not a gate test; Protocol Section 6.3)
Domain | Current level (1–4) | Target level (1–4) | Gap | Priority (H/M/L) | Notes |  | Level 1: Traditional | Level 2: Emerging | Level 3: Integrated | Level 4: Optimized
Metering and meter data | [6 empty] | Manual reading; no interval data | Some AMR/AMI; data in silos | AMI with MDMS and VEE feeding billing | AMI data used enterprise-wide in real time
Network visibility and automation | [6 empty] | No feeder or transformer monitoring | Substation SCADA only | Feeder monitoring; some automated switching | Automated fault isolation and restoration
Customer service | [6 empty] | Walk-in and phone only | Basic SMS and online bill access | Usage data access; digital self-service | Personalized programs; proactive outage messages
Analytics and decision support | [6 empty] | Spreadsheet reports | Standard system reports | Loss, load, and voltage analytics in use | Predictive analytics drive planning and maintenance
IT/OT integration | [6 empty] | Stand-alone systems | Point-to-point interfaces | Standards-based integration (e.g., CIM) | Integrated data platform with governance
DER and future readiness | [6 empty] | No visibility of rooftop solar or EVs | Net-metering records only | Hosting capacity tracked; bidirectional data used | DER actively managed

## A2 Baseline KPIs
A2: Operational Baseline
Stage A · Protocol Section 6 and Annex D.1. Measure over at least 12 months where records allow. The same definitions are used in the pilot and in operations.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
KPI | Definition | Numerator / value | Denominator | Result | Unit | Period covered | Data source | Data-quality note | Required for Gate 1
System loss rate | (Energy purchased or received − energy sold) ÷ energy purchased or received, 12-month rolling. Enter kWh lost as numerator. |  |  |  | % |  |  |  | Must
Estimated-bill rate | Bills whose billing determinants were estimated ÷ bills issued (Protocol 21.1) |  |  |  | % |  |  |  | Must
Billing accuracy | Bills needing no correction within 90 days for metering, data, or billing error ÷ bills issued (Protocol 21.1) |  |  |  | % |  |  |  | Must
Billing-read availability | Accounts with a validated actual read at billing cut-off ÷ accounts billed (Protocol 21.1) |  |  |  | % |  |  |  | Must
Transformer-level loss (pilot-area sample) | Protocol 21.3 method: (transformer energy − customer energy − estimated technical loss) ÷ transformer energy. Enter non-technical kWh as numerator, transformer kWh as denominator |  |  |  | % |  |  |  | Must if business case depends on loss
Meter reading cost per account | Total reading cost (labor, transport, devices) ÷ accounts read |  |  |  | PHP |  |  |  | Must
Billing complaints per 1,000 accounts | Billing and meter complaints per month ÷ accounts × 1,000 |  |  |  | per 1,000 |  |  |  | Must
Average complaint resolution time | Mean working days from receipt to closure (enter the value as numerator; leave denominator blank) |  |  |  | value |  |  |  | Must
Cost per disconnection/reconnection field order | Total field order cost ÷ number of orders |  |  |  | PHP |  |  |  | Should
Payment-to-reconnection time | Mean hours from payment to reconnection (enter the value as numerator) |  |  |  | value |  |  |  | Should
Meter-to-transformer mapping accuracy | Sampled accounts correctly mapped ÷ accounts sampled (field-verified) |  |  |  | % |  |  |  | Must (pilot areas)
Collection efficiency | Collections ÷ billings for the period |  |  |  | % |  |  |  | Should
SAIFI | As defined in the Philippine Distribution Code (enter value) |  |  |  | value |  |  |  | Should
SAIDI | As defined in the Philippine Distribution Code (enter value) |  |  |  | value |  |  |  | Should

## A4 Workforce Matrix
A4: Workforce Capability Matrix
Stages A and M · Protocol Section 12 (W1). Rate capability 1 (none) to 4 (fully capable). Gap drives the training and staffing plan.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Function | AMI-related capability required | Current (1–4) | Required (1–4) | Gap | Training or hiring needed | Staff affected (no.) | Role changes (e.g., meter reader redeployment) | Owner | Due date
Engineering | Communication design, transformer balancing, voltage analysis
Metering | Smart meter testing, installation, commissioning, tamper investigation
IT | HES/MDMS administration, integration, data management
Billing | VEE exception handling, billing determinants, reconciliation
Consumer services | AMI inquiries, usage data, complaint handling
Field operations | Installation, fault response, safety
Cybersecurity | Security monitoring, access control, incident response
Finance | Business case, asset accounting, benefits tracking
Loss reduction | Analytics-led inspection and enforcement
Regulatory affairs | ERC/NEA applications and reporting

## M1 Comms Scoring
M1: Communication Technology Evaluation
Stage M · Protocol Section 15.4. Score each option 1 (poor) to 5 (excellent) from field-survey evidence, not vendor claims. Copy this sheet for each distinct area type (e.g., urban, rural, island).
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Area type evaluated:
Criterion | What to assess | Weight | PLC | RF mesh | Cellular | Hybrid | Evidence reference
Coverage | Share of surveyed meter points reachable with design link margin | 20%
Performance | Read success and latency in survey or trial | 15%
Lifecycle cost per meter | One-time plus recurring cost over asset life | 20%
Resilience | Typhoon exposure, backup power, flood risk at collector sites | 10%
Scalability | Capacity for full deployment and future devices | 10%
Security | Encryption, authentication, key management, patchability | 10%
Standards and interoperability | Open standards; multi-vendor options | 5%
Local support | Vendor and local capability to install and maintain | 5%
Regulatory and carrier dependencies | NTC compliance; carrier SLAs; network shutdown risk | 5%
Total weight (must equal 100%) |  | 100%
Weighted score (out of 5) |  |  | Incomplete | Incomplete | Incomplete | Incomplete
Rank
Weights shown are Metro Power suggested starting weights; the TWG should confirm them before scoring. Default weights are blue inputs and may be changed.

## M2 Business Case
M2: Business Case Model (PHP)
Stages M and E1 · Protocol Section 19 and Annex G. Enter nominal annual cash amounts in pesos. Year 0 is the investment year. Record every assumption in M3.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Enter costs and benefits incremental to the do-nothing option (continuing current metering). Enter only benefits marked “Counted = Yes” in M4. Record every assumption in M3.
Discount rate (utility-approved; state real or nominal and keep cash flows consistent)
Annual kWh sales (for rate impact)
Average residential consumption (kWh/month)
Memo (non-cash): undepreciated book value of legacy meters to be retired (PHP)
COMPONENT LIFE AND SCHEDULED REPLACEMENT (Protocol Section 20.3) |  |  | Enter expected life from vendor commitments, carrier notices, and utility experience; record sources in M3. Replacement cost is scheduled automatically in each year that is a multiple of the life.
Component | Expected life (years) | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Total | Quantity | Unit replacement cost (PHP)
Meter body and metrology |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Communication module |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Battery (where fitted) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Concentrators and collectors |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Backhaul equipment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HES/MDMS software refresh |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Servers and hosting refresh |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other component |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Line item | Type | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Total
COSTS
Meters, modules, and service switches | One-time | [16 empty] | 0
Network: concentrators, collectors, backhaul build | One-time | [16 empty] | 0
HES, MDMS, CMDC and other software (one-time) | One-time | [16 empty] | 0
Integration and data migration | One-time | [16 empty] | 0
Installation, mapping verification, and quality control | One-time | [16 empty] | 0
Program management, training, consumer engagement, workforce transition | One-time | [16 empty] | 0
Security and privacy (one-time) | One-time | [16 empty] | 0
Legacy meter removal and disposal | One-time | [16 empty] | 0
Software subscriptions, licenses, hosting | Recurring | [16 empty] | 0
Cellular and backhaul data charges | Recurring | [16 empty] | 0
Maintenance and vendor support | Recurring | [16 empty] | 0
Internal operations staff | Recurring | [16 empty] | 0
Security monitoring and testing | Recurring | [16 empty] | 0
Scheduled component replacements (from table above) | Lifecycle (auto) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Failure replacements and other lifecycle costs | Lifecycle | [16 empty] | 0
Financing costs (interest, fees) | Financial | [16 empty] | 0
Foreign-exchange contingency | Financial | [16 empty] | 0
Contingency | One-time | [16 empty] | 0
Total costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BENEFITS
Non-technical loss reduction (value of energy recovered) | Benefit | [16 empty] | 0
Meter-reading cost avoided | Benefit | [16 empty] | 0
Field visits avoided (disconnect/reconnect, re-reads) | Benefit | [16 empty] | 0
Billing error and dispute cost reduction | Benefit | [16 empty] | 0
Collection improvement (financing value) | Benefit | [16 empty] | 0
Outage and operational savings | Benefit | [16 empty] | 0
Asset and planning value (deferred capital, avoided failures) | Benefit | [16 empty] | 0
Residual value of assets (enter in final year only) | Benefit | [16 empty] | 0
Benefit realization ramp (% of full benefit; blank = 100%) | Ramp
Total benefits (after ramp) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net cash flow |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Discount factor |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Discounted net cash flow |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative net cash flow |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Payback flag (helper) |  | 0
RESULTS
Net present value (PHP) | Enter discount rate
Internal rate of return | n/a
Payback year (simple, undiscounted) | n/a
Indicative rate impact (PHP/kWh), year 1 net cost | Enter kWh sales
Indicative impact on average residential monthly bill (PHP)
Rate impact here is a simple indicator (net year-1 cost ÷ kWh sales). Actual rate impact follows the applicable ERC rate methodology and must be computed by the utility's regulatory team.
SENSITIVITY
Scenario | Cost multiplier | Benefit multiplier | NPV (PHP)
Base | 1 | 1
Costs +20% | 1.2 | 1
Benefits −25% | 1 | 0.75
Costs +20% and benefits −25% | 1.2 | 0.75
Benefits delayed one year (costs unchanged) | 1 | shift +1 yr
OPTIONS COMPARISON (run a copy of this sheet for each option)
Option | Description | NPV (PHP) | IRR | Key risks
Do nothing (continue current metering)
Option A
Option B
Option C

## M3 Assumptions
M3: Assumptions Register
Stages M and E1 · Protocol Section 19. Every number in the business case should trace to a row here, with its source type.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
ID | Assumption | Value | Unit | Source type | Source reference | Low | High | Used in (sheet/line) | Owner | Last updated
EXAMPLE A-01 | Installation cost per single-phase meter |  | PHP/meter | Vendor quotation | Quotation ref. and date |  |  | M2 · Installation | Program Manager
Rule (Protocol 5.1, 19.1): an unverified vendor claim cannot support a Must criterion or a benefit counted in the business case.

## M4 Benefit Mapping
M4: Benefit Mapping (Asset → Function → Benefit → Beneficiary)
Stages M and E1 · Protocol Sections 19.3–19.4 and Annex G.3 (EU JRC method). A benefit is counted only if its baseline is measured, its enabling function is in the design, and it has a named owner.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Asset | Function enabled | Benefit | Beneficiary | Monetized in M2? (Y/N) | M2 line | Baseline KPI (A2) | Function in approved design? (Y/N) | Benefit owner | Counted in business case?
Smart meters + communications | Remote interval and register reading | Meter-reading cost avoided | Utility; consumers through rates |  | Meter-reading cost avoided | Meter reading cost per account |  |  | No, see Protocol 19.3
Smart meters + communications | Remote reading; VEE in MDMS | Fewer estimated and corrected bills | Consumers; utility |  | Billing error and dispute cost reduction | Estimated-bill rate; billing adjustment rate |  |  | No, see Protocol 19.3
Transformer meters + mapping + MDMS analytics | Transformer energy balancing | Non-technical loss reduction | Utility; paying consumers |  | Non-technical loss reduction (value of energy recovered) | System loss rate; mapping accuracy |  |  | No, see Protocol 19.3
Smart meters (tamper sensing) | Tamper and anomaly events | Targeted inspections; loss reduction | Utility |  | Non-technical loss reduction (value of energy recovered) | System loss rate |  |  | No, see Protocol 19.3
Service switch + HES | Remote disconnect and reconnect (within safeguards) | Field visits avoided; faster reconnection | Utility; consumers |  | Field visits avoided (disconnect/reconnect, re-reads) | Cost per field order; payment-to-reconnection time |  |  | No, see Protocol 19.3
Service switch + prepaid functions | Prepaid service | Collection improvement; consumer budgeting | Utility; consumers |  | Collection improvement (financing value) | Collection efficiency |  |  | No, see Protocol 19.3
Smart meters + OMS integration | Last-gasp and restoration events | Faster outage detection and restoration verification | Consumers; utility |  | Outage and operational savings | SAIFI; SAIDI |  |  | No, see Protocol 19.3
Smart meters + MDMS | Transformer loading from aggregated interval data | Avoided transformer failures; deferred capital | Utility; consumers through rates |  | Asset and planning value (deferred capital, avoided failures) |  |  |  | No, see Protocol 19.3
Smart meters (voltage) | Voltage monitoring | Voltage compliance; fewer complaints | Consumers; utility |  | Outage and operational savings |  |  |  | No, see Protocol 19.3
CMDC and consumer channels | Consumer access to usage data | Consumer awareness and choice | Consumers | [5 empty] | No, see Protocol 19.3
Bidirectional meters | Net-metering measurement | Accurate credits; DER visibility | Consumers; society | [5 empty] | No, see Protocol 19.3
Interval data | Load research | Better tariff and demand forecasting | Utility; consumers | [5 empty] | No, see Protocol 19.3
Non-monetary effects (Protocol Section 19.4), reported alongside, never added to, financial results
Effect | What to assess | Expected direction (+ / − / neutral) | Evidence | Owner
Safety | Field-worker and public safety; fewer manual disconnections
Privacy | Residual risk after controls (from PIA)
Consumer acceptance and trust | Complaints, surveys, community feedback
Fairness | Effects on low-income, vulnerable, and prepaid consumers
Workforce | Roles changed or redeployed; skills gained
Environment and energy transition | Support for net metering, rooftop solar, demand response
Resilience | Outage visibility in typhoons; restoration verification

## M5 Requirements Compliance
M5: Requirements Compliance Evaluation
Stage M (tender evaluation) and Stage P · Protocol Annex E. Record each bidder’s compliance with evidence. C = compliant, P = partial, N = non-compliant, NA = not applicable.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
|  |  | Bidder names → | Bidder A |  | Bidder B |  | Bidder C
Req. ID | Area | Requirement | Mandatory? (Y/N) | A: C/P/N/NA | A: evidence | B: C/P/N/NA | B: evidence | C: C/P/N/NA | C: evidence
RQ-001 | Smart Meters | ERC type approval held before any meter is installed (ERC Res. No. 16, s. 2017); a documented path to type approval is acceptable at tender but not at installation | Y
RQ-002 | Smart Meters | Tested and sealed as required by ERC rules before installation | Y
RQ-003 | Smart Meters | Product safety to IEC 62052-31 | Y
RQ-004 | Smart Meters | Accuracy class per segment (Section 15.1), certified by an accredited laboratory | Y
RQ-005 | Smart Meters | IEC 62056 (DLMS/COSEM) or ANSI C12.18/19/22 data model and protocol | Y
RQ-006 | Smart Meters | Interval data at configurable resolution; minimum on-board storage defined | Y
RQ-007 | Smart Meters | Event log: power off/on, tamper, cover open, magnetic, reverse energy, voltage events | Y
RQ-008 | Smart Meters | Integrated service switch where remote connect/disconnect is in scope; rated for the service | Y
RQ-009 | Smart Meters | Bidirectional measurement for net-metering customers, with separate import and export registers and interval channels, and capacity for additional channels for distributed energy resources | Y
RQ-010 | Smart Meters | Prepaid functionality where in scope, consistent with ERC prepaid rules | Y
RQ-011 | Smart Meters | Signed firmware, secure boot where supported, over-the-air update | Y
RQ-012 | Smart Meters | Real-time clock with synchronization; drift no more than 0.5 seconds per day (IEC 62054-21); within ±5 seconds of reference after synchronization | Y
RQ-013 | Smart Meters | Environmental rating suitable for local heat, humidity, and salt exposure; surge withstand specified | Y
RQ-014 | Smart Meters | Supports STS (IEC 62055-41) Edition 2 or later, including the post-2024 token identifier range and key change by token, where token-based prepaid is in scope; payment meter requirements to IEC 62055-31 | Y
RQ-015 | Smart Meters | Interoperability conformance certificates (for example DLMS User Association, Wi-SUN Alliance) where those standards are specified | Y
RQ-016 | Smart Meters | Meter identifier compatible with the national meter identifier scheme once issued (Section 25.1); GPS position recorded at installation | Y
RQ-017 | Smart Meters | For cellular meters: replaceable communication module, multi-carrier capability or eSIM, and LTE-M/Cat-M or NB-IoT support where available | Y
RQ-018 | Communications | Technology selected on Stage M field survey evidence | Y
RQ-019 | Communications | Design link margin defined per technology and validated in the field | Y
RQ-020 | Communications | Concentrator or collector backup power duration specified and tested at SAT | Y
RQ-021 | Communications | Hardening for typhoon and flood exposure at collector and concentrator sites | Y
RQ-022 | Communications | NTC equipment authorization and frequency compliance for radio and cellular equipment | Y
RQ-023 | Communications | Encryption and device authentication on the field network | Y
RQ-024 | Communications | Carrier service levels and network-shutdown notice terms for cellular; private APN or VPN | Y
RQ-025 | Communications | Outage event capture target set for each technology (Section 21.1) | Y
RQ-026 | Communications | Store-and-forward or satellite backhaul options for off-grid and island areas (Section 15.7) | Y
RQ-027 | Head-End System | Supports all meter types and communication technologies in the architecture; multi-vendor support demonstrated where specified | Y
RQ-028 | Head-End System | Scheduled and on-demand reads; command queuing with confirmation | Y
RQ-029 | Head-End System | Authorization controls, rate limits, and time-window blocking for disconnect commands, with permitted windows, notice periods, and holiday calendar held as configurable parameters | Y
RQ-030 | Head-End System | On a shared platform, a platform-wide disconnect cap in addition to each tenant’s cap | Y
RQ-031 | Head-End System | Firmware and configuration management with staged rollout and rollback | Y
RQ-032 | Head-End System | Key and certificate management under utility control, including wrapped key import and replacement of manufacturing keys after commissioning (Section 16.1) | Y
RQ-033 | Head-End System | Documented APIs to MDMS and other systems (IEC 61968-9 or MultiSpeak preferred) | Y
RQ-034 | Head-End System | Availability and performance service levels | Y
RQ-035 | Head-End System | One-step suspension of disconnections by area for calamities | Y
RQ-036 | Head-End System | Time synchronization from a source traceable to Philippine Standard Time or GNSS-disciplined authenticated NTP; timestamps exchanged in UTC (Section 18.7) | Y
RQ-037 | Meter Data Management and Billing Integration | Configurable validation rules covering Section 18.2 | Y
RQ-038 | Meter Data Management and Billing Integration | Estimation methods and controls per Section 18.3 | Y
RQ-039 | Meter Data Management and Billing Integration | Editing with full audit trail and dual approval above thresholds | Y
RQ-040 | Meter Data Management and Billing Integration | Automated reconciliation between HES, MDMS, and CIS | Y
RQ-041 | Meter Data Management and Billing Integration | Billing determinants delivered to CIS before cut-off with exception reporting | Y
RQ-042 | Meter Data Management and Billing Integration | Data export of all data in documented non-proprietary formats | Y
RQ-043 | Meter Data Management and Billing Integration | CMDC and consumer access interfaces per ERC requirements | Y
RQ-044 | Meter Data Management and Billing Integration | Capacity for full deployment volume with defined growth headroom | Y
RQ-045 | Meter Data Management and Billing Integration | Validation for CT/VT multiplier errors, reverse energy on non-net-metered accounts, meter-exchange continuity, and outage-aware zero consumption | Y
RQ-046 | Meter Data Management and Billing Integration | Disaster recovery with documented recovery point and recovery time objectives, tested | Y
RQ-047 | Outage and Network Integration | Last-gasp and restoration events delivered to OMS or dispatch | Y
RQ-048 | Outage and Network Integration | Restoration verification by meter ping | Y
RQ-049 | Outage and Network Integration | Transformer and feeder aggregation using the GIS network model | Y
RQ-050 | Outage and Network Integration | Voltage event reporting to engineering | Y
RQ-051 | Supply Chain and Vendor Access | Software bill of materials for meter firmware, HES, and MDMS, updated with each release | Y
RQ-052 | Supply Chain and Vendor Access | A published vulnerability disclosure process and a commitment to notify the utility of vulnerabilities affecting its systems within a defined period | Y
RQ-053 | Supply Chain and Vendor Access | Firmware signing keys protected in a hardware security module under the supplier’s documented controls, with a revocation process | Y
RQ-054 | Supply Chain and Vendor Access | Vendor remote access only through a utility-controlled jump host, with multi-factor authentication, session approval, and session logging | Y
RQ-055 | Supply Chain and Vendor Access | Disclosure of hosting locations, subcontractors, and any access to data from outside the Philippines (Section 16.2) | Y
RQ-056 | Supply Chain and Vendor Access | Security patches supported for the contract term and a stated end-of-support notice period | Y
|  | Mandatory requirements not met (N) |  | 0 |  | 0 |  | 0
|  | Requirements not yet assessed |  | 56 |  | 56 |  | 56
Unverified vendor claims are not evidence of compliance (Protocol 5.1). Cite certificates, test reports, or reference-site data.

## P1 Pilot KPI Tracker
P1: Pilot Evaluation Plan and KPI Tracker
Stages M and P · Protocol Sections 8.6, 21.1 and Annex C.1. Thresholds and non-inferiority margins are fixed at Gate 2. Enter each stratum’s measurement-period result and the size of each denominator. Must-Pass KPIs must pass in every stratum to which the gate decision applies.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Design effect used for bounds |  | 1.5 | [7 empty] | Stratum names → | Stratum 1 | Stratum 2 | Stratum 3 | Stratum 4
One-sided z (95%) |  | 1.645 | [7 empty] | n: meters measured →
n: bills measured →
n: commands issued →
[10 empty] | Census stratum? (Y/N) → | N | N | N | N
ID | Hypothesis | KPI | Dir. | Threshold | Non-inferiority margin | Denominator | Unit | Designation | Judged at | Baseline | S1 result | S2 result | S3 result | S4 result | S1 status | S2 status | S3 status | S4 status | Overall | Data source / verified by
H1 | AMI delivers interval data reliably | Daily read success rate (≥95% of intervals by 06:00) | ≥ | 98% | 1% | meters | % | Must-Pass | Gate 3 | [9 empty] | Pending
H1 |  | Billing-read availability | ≥ | 99% |  | meters | % | Monitor | Not gated | [9 empty] | Pending
H2 | AMI bills are correct | Register-read reconciliation (matched within ±1 display digit ÷ sampled; ≥50 per stratum per cycle) | ≥ | 100% |  | meters | % | Must-Pass | Gate 3 | [9 empty] | Pending
H2 |  | Billing accuracy (no correction within 90 days) | ≥ | 99.5% | 0.2% | bills | % | Must-Pass | Gate 4 | [9 empty] | Pending
H3 | AMI removes routine estimation | Estimated-bill rate (estimated determinants) | ≤ | 1% | 0.5% | bills | % | Must-Pass | Gate 4 | [9 empty] | Pending
H4 | Remote operations are reliable and safe | Remote command success (first attempt, within latency class 5 or 60 min; Must-Pass only if remote switching is in scope) | ≥ | 95% | 2% | commands | % | Must-Pass | Gate 3 | [9 empty] | Pending
H4 |  | Firmware update success (if a campaign runs) | ≥ | 95% |  | meters | % | Monitor | Not gated | [9 empty] | Pending
H5 | Systems are secure and available | Unresolved security findings, as defined for each gate (Protocol 21.1), from P6 gate checks | ≤ | 0 |  | n/a | count | Must-Pass | Gates 3, 4, 5 | [9 empty] | Pending
H5 |  | HES and MDMS availability | ≥ | 99.5% |  | n/a | % | Monitor | Not gated | [9 empty] | Pending
H6 | Outages are detected | Outage event capture (target set by technology) | ≥ | 95% |  | n/a | % | Monitor | Not gated | [9 empty] | Pending
H7 | Consumers are served well | Complaints acknowledged within 24 hours | ≥ | 95% |  | n/a | % | Monitor | Not gated | [9 empty] | Pending
H7 |  | Average resolution, standard complaints | ≤ | 5 |  | n/a | working days | Monitor | Not gated | [9 empty] | Pending
H7 |  | Meter-test turnaround | ≤ | 10 |  | n/a | working days | Monitor | Not gated | [9 empty] | Pending
H7 |  | Consumer satisfaction (survey) | ≥ | 85% |  | n/a | % | Monitor | Not gated | [9 empty] | Pending
H8 | AMI supports loss reduction | Reduction in estimated non-technical loss rate vs transformer baseline, percentage points (21.3) | ≥ |  |  | n/a | pp | Must-Pass | Gate 4 | [9 empty] | Pending
H9 | Operating costs fall | Meter-reading cost per account | ≤ |  |  | n/a | PHP | Monitor | Not gated | [9 empty] | Pending
Summary
| Must-Pass KPIs | 7 |  | Must-Pass not met in Stratum 1 |  |  |  | 0
| Must-Pass not met in at least one stratum | 0 |  | Must-Pass not met in Stratum 2 |  |  |  | 0
| Must-Pass inconclusive, pending, or incomplete | 7 |  | Must-Pass not met in Stratum 3 |  |  |  | 0
| All Must-Pass KPIs passed in all strata? | Not yet |  | Must-Pass not met in Stratum 4 |  |  |  | 0
| Must-Pass rate KPIs without a margin (set at Gate 2) | 0
Pass rule (Protocol 8.6): MET when the result meets the threshold AND the one-sided 95% bound (with design effect, on the KPI’s own denominator) is no worse than threshold − margin. Result meets threshold but bound does not = INCONCLUSIVE (extend or enlarge). Census strata, 100% or zero targets, and counts are judged on the result alone.
Default margin equals the precision used to size the stratum: 1 point for the default sample (P2), 2 points on the lean path. Margins for bill- and command-based KPIs are illustrative and must be fixed in the Pilot Evaluation Plan at Gate 2. Low-volume segments (e.g., CT-connected meters) use P5 functional tests and 100% reconciliation. With pooled sector evidence, enter the combined n.
Must-Pass KPIs, thresholds, and margins may be changed after Gate 2 only by the Board, never after results are known; record every change in P7. Defaults are provisional Metro Power recommendations, not service standards; ERC standards prevail.

## P2 Site & Sampling
P2: Pilot Site Selection and Sample Design
Stage M · Protocol Section 8.6. Default: ±1 point with design effect 1.5 (about 1,130 meters per stratum). Lean path with approval: ±2 points (about 280 meters).
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Selection criterion | Weight | Area A | Area B | Area C | Area D | Notes
Represents consumer mix of full deployment | 20%
Includes difficult communication conditions | 15%
Historical system loss (baseline measurable) | 15%
Meter-to-transformer mapping verifiable | 15%
Load diversity (residential, commercial, industrial) | 10%
Field accessibility and safety | 10%
Barangay/LGU support | 10%
Operational visibility needs (outages, voltage) | 5%
Total weight / weighted score (1–5) | 100%
Sample size calculator (per stratum)
Parameter | Value | Explanation
Expected rate (p) | 98% | Expected value of the KPI, e.g., read success rate
Margin of error (e) | 1% | ± precision required, as a fraction
Confidence level | 95% | Choose 90%, 95%, or 99%
Design effect | 1.5 | Inflation for clustering by area or concentrator (1.0 = none; 1.5–2.0 typical when failures cluster)
z value | 1.96
Minimum meters in the stratum | 1130 | Values shown are an illustration (98% ± 1 point at 95% confidence, design effect 1.5). Without clustering (design effect 1.0) the answer is 753.
Meters in the stratum (N), if small |  | Leave blank for large strata. Used for the finite-population correction.
Sample after finite-population correction | 1130
Recommendation | Sample (large stratum) | Protocol 8.6: census where the stratum has fewer than 300 meters or the corrected sample exceeds about 70% of it.
Pilot strata
Customer segment | Meter type | Communication technology | Area type | Meters planned | Minimum required (after correction) | Adequate? | Comparison (non-pilot) area | Census? (Y/N)

## P3 Pilot Budget
P3: Pilot Budget and Cost Record
Stages M and P · Protocol Sections 7 and 8 (deliverable P-5). Record actual costs, including internal labor, so the final business case uses real figures.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Budget category | Approved budget (PHP) | Committed (PHP) | Actual to date (PHP) | Variance vs budget (PHP) | Funding source | Remarks
Smart meters and modules
Communication infrastructure
HES and MDMS (licenses, hosting)
Integration (CIS, OMS, GIS, CMDC)
Installation labor and logistics
Mapping verification and field surveys
Testing (FAT, SAT, security testing)
Cybersecurity controls
Training
Consumer engagement and education
Project management
Internal staff time (costed)
Contingency
Total | 0 | 0 | 0 | 0
Actual as % of budget

## P4 Program Plan
P4: Program Plan (Stages A to E1)
All stages · Protocol Sections 5–9. Replace the indicative activities with the utility's plan. Durations calculate from dates.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Stage | Activity | Owner | Start | Finish | Days | Status | Depends on | Deliverable / gate | Remarks
A | Constitute Steering Committee and TWG; receive advisor disclosures (T10) |  |  |  |  | Not started
A | Agree AMI objectives |  |  |  |  | Not started |  | A-4
A | Readiness assessment and executive workshop |  |  |  |  | Not started |  | A-1
A | Measure operational baseline |  |  |  |  | Not started |  | A-2
A | Meter and systems inventory |  |  |  |  | Not started |  | A-3
A | Gap closure plan |  |  |  |  | Not started |  | A-5
A | Transformer meters on pilot-area sample (if loss benefit) |  |  |  |  | Not started |  | Baseline
A | Gate 1 decision |  |  |  |  | Not started |  | Gate 1
M | Requirements specification |  |  |  |  | Not started |  | M-1
M | Communication field survey and feasibility study |  |  |  |  | Not started |  | M-2
M | Solution and security architecture |  |  |  |  | Not started |  | M-3
M | Privacy Impact Assessment |  |  |  |  | Not started |  | M-4
M | Preliminary business case |  |  |  |  | Not started |  | M-5
M | Pilot Evaluation Plan |  |  |  |  | Not started |  | M-6
M | Procurement package |  |  |  |  | Not started |  | M-7
M | Independent specification review for vendor bias (Protocol 13.3) |  |  |  |  | Not started |  | Before issue
M | Pilot consumer engagement plan |  |  |  |  | Not started |  | M-8
M | Data Migration and Cleansing Plan |  |  |  |  | Not started |  | M-9
M | Early engagement with the ERC and, for ECs, the NEA on approach |  |  |  |  | Not started
M | Independent gate review (T9) |  |  |  |  | Not started |  | Before Gate 2
M | Gate 2 decision (Board) |  |  |  |  | Not started |  | Gate 2
P | Procurement and contract award |  |  |  |  | Not started
P | Factory Acceptance Testing |  |  |  |  | Not started |  | P-1
P | Consumer notification in pilot areas |  |  |  |  | Not started
P | Installation and mapping verification |  |  |  |  | Not started |  | P-2
P | Site Acceptance and integration testing |  |  |  |  | Not started |  | P-1
P | Security testing |  |  |  |  | Not started |  | P-3
P | Pilot operation (≥ 3 billing cycles) |  |  |  |  | Not started |  | P-4
P | Gate 3 technical acceptance |  |  |  |  | Not started |  | Gate 3
E1 | Pilot evaluation and data-quality review |  |  |  |  | Not started |  | E-1
E1 | Final business case |  |  |  |  | Not started |  | E-2
E1 | Rollout strategy |  |  |  |  | Not started |  | E-3
E1 | Regulatory application package |  |  |  |  | Not started |  | E-4
E1 | Consumer and member consultation on program and rate impact (Protocol 17.7) |  |  |  |  | Not started |  | Gate 4 Must
E1 | Workforce Transition Plan with employee/union consultation (Protocol 12.1) |  |  |  |  | Not started |  | Gate 4 Must
E1 | ERC, supervising-agency, and lender approvals; conditional rollout contracts (Protocol 9.7) |  |  |  |  | Not started |  | Gate 4 Must
E1 | Board decision paper |  |  |  |  | Not started |  | E-5
E1 | Independent gate review (T9) |  |  |  |  | Not started |  | Before Gate 4
E1 | Gate 4 investment decision (Board) |  |  |  |  | Not started |  | Gate 4

## P5 Acceptance Tests
P5: Acceptance Test Catalog
Stage P · Protocol Section 8 and Annex E. Starting catalog: adapt test methods and criteria to the contract specification. Every failed test gets an entry in P6 (functional defect or security finding).
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Test ID | Phase | Category | Test | Method (summary) | Acceptance criterion | Result | Date | Tester / witness | Defect ref. | Summary phase | Tests | Pass | Fail | Not run
TC-001 | FAT | Meter | Accuracy at test points of the accuracy class | Reference-standard test at the load points defined by the applicable standard (IEC 62053 / ANSI C12.20) | Errors within class limits at all points | Not run |  |  |  | Tender | 1 | 0 | 0 | 1
TC-002 | FAT | Meter | Starting current and no-load (creep) | Apply starting current; apply voltage with no load | Registers at starting current; no creep | Not run |  |  |  | Receiving | 1 | 0 | 0 | 1
TC-003 | FAT | Meter | Voltage and frequency variation | Vary within specified ranges | Errors within limits; no resets | Not run |  |  |  | FAT | 15 | 0 | 0 | 15
TC-004 | FAT | Meter | Display vs communicated register | Compare display with value read through HES | Identical values | Not run |  |  |  | SAT | 10 | 0 | 0 | 10
TC-005 | FAT | Meter | Real-time clock accuracy | Compare with reference after drift period | Drift ≤ 0.5 s/day (IEC 62054-21); ±5 s after sync | Not run |  |  |  | Integration | 26 | 0 | 0 | 26
TC-006 | FAT | Meter | Load profile storage and retention | Record profile; power down; retrieve | Complete profile retained for specified days | Not run |  |  |  | Security | 10 | 0 | 0 | 10
TC-007 | FAT | Meter | Event log capture | Trigger power fail, restore, voltage events | All events logged with correct timestamps | Not run |  |  |  | Performance | 2 | 0 | 0 | 2
TC-008 | FAT | Meter | Tamper: main cover and terminal cover open | Open covers under power and without power | Event raised and communicated | Not run |  |  |  | UAT | 4 | 0 | 0 | 4
TC-009 | FAT | Meter | Tamper: magnetic interference | Apply magnet per specification | Event raised; accuracy behavior as specified | Not run |  |  |  | Pilot | 2 | 0 | 0 | 2
TC-010 | FAT | Meter | Tamper: reverse current and neutral disturbance | Reverse connection; remove neutral; earth load | Event raised; energy registered as specified | Not run
TC-011 | FAT | Meter | Service switch operation | Connect/disconnect/reconnect at rated current, repeated | Operates every time; status reported correctly | Not run
TC-012 | FAT | Meter | Unsigned firmware rejected | Attempt to load unsigned or altered firmware | Rejected and event logged | Not run
TC-013 | FAT | Meter | Bidirectional registers (net metering) | Apply import and export | Separate registers correct | Not run
TC-014 | FAT | Meter | Prepaid credit behavior | Credit exhaustion, top-up, emergency credit, friendly hours | Behaves per specification and ERC prepaid rules | Not run
TC-015 | FAT | Meter | STS token handling and keys (if token prepaid) | Load valid, duplicate, expired, and wrong-supply-group tokens; key change tokens; tokens with identifiers in the post-November-2024 range | Valid tokens only accepted; key change works; post-2024 token identifiers accepted; vending keys from the KMC under utility control | Not run
TC-016 | Receiving | Logistics | Lot receiving inspection | Sample incoming lot per the acceptance-sampling plan | Defects within the acceptance number | Not run
TC-017 | Tender | Documents | Type approval and certificates | Review ERC type approval and accredited lab reports at bid evaluation, and again for each delivered lot | Valid type approval for every model and firmware before installation | Not run
TC-018 | SAT | Communications | Read success by area (commissioning check) | Collect daily reads for one full billing cycle after commissioning, before the measurement period starts | Trending to the P1 threshold in every stratum; the formal result comes from the measurement period | Not run
TC-019 | SAT | Systems | Clock synchronization | Check meter clocks against the HES reference after synchronization | Within ±5 seconds; HES time source traceable | Not run
TC-020 | SAT | Resilience | Disaster recovery of HES/MDMS | Fail over or restore to the recovery site | Recovered within the specified recovery time; data loss within the recovery point | Not run
TC-021 | SAT | Documents | Interoperability certificates | Review DLMS UA, Wi-SUN, or other certificates required by the specification | Valid certificates for the supplied models and firmware | Not run
TC-022 | SAT | Communications | On-demand read latency | Sample on-demand reads across areas | Within specified time | Not run
TC-023 | SAT | Communications | Recovery after power outage | Simulate area outage and restoration | Devices rejoin and reads resume within specified time | Not run
TC-024 | SAT | Communications | Collector/concentrator backup power | Remove mains supply | Operates for specified duration | Not run
TC-025 | SAT | Communications | Weak-signal and difficult areas | Test worst surveyed locations | Link margin met or mitigation installed | Not run
TC-026 | SAT | Communications | Backhaul failover | Disconnect primary backhaul | Traffic moves to secondary if specified | Not run
TC-027 | SAT | Installation | Mapping and seal records | Audit sample of installations | 100% of sample has correct mapping, GPS, photo, and seal records | Not run
TC-028 | Integration | HES | Scheduled and on-demand reads | Run schedules; issue on-demand reads | Complete and correct | Not run
TC-029 | Integration | HES | Command confirmation | Issue connect/disconnect; verify status | Status confirmed; failures flagged | Not run
TC-030 | Integration | HES | Disconnect time-window blocking | Attempt disconnect outside permitted windows | Command blocked and logged | Not run
TC-031 | Integration | HES | Calamity suspension by area | Activate one-step suspension of disconnections for an area | All disconnections in the area blocked until lifted | Not run
TC-032 | Integration | HES | Account-to-meter verification before disconnect | Attempt disconnect where account and meter records disagree | Command blocked pending verification | Not run
TC-033 | Integration | HES | Bulk command rate limit | Attempt mass disconnect above limit | Blocked; alert raised | Not run
TC-034 | Integration | HES | Firmware campaign | Staged rollout with rollback | Target success rate met; rollback works | Not run
TC-035 | Integration | HES | Key rotation | Rotate device keys | Communication continues; old keys invalid | Not run
TC-036 | Integration | MDMS/VEE | Missing and duplicate data detection | Inject gaps and duplicates | Detected and handled per rules | Not run
TC-037 | Integration | MDMS/VEE | Negative, zero, and spike detection | Inject anomalous data | Flagged per rules | Not run
TC-038 | Integration | MDMS/VEE | Estimation methods | Force estimation cases | Correct method applied and flagged on bill | Not run
TC-039 | Integration | MDMS/VEE | Manual edit controls | Edit data above and below threshold | Audit trail complete; dual approval enforced | Not run
TC-040 | Integration | MDMS/VEE | Register vs interval sum | Compare register delta with interval total | Within specified tolerance | Not run
TC-041 | Integration | MDMS/VEE | Multiplier error detection | Inject consumption inconsistent with the CT/VT multiplier | Flagged for review | Not run
TC-042 | Integration | MDMS/VEE | Reverse energy on non-net-metered account | Inject export on an import-only account | Flagged for investigation | Not run
TC-043 | Integration | MDMS/VEE | Meter-exchange continuity | Process a meter exchange | Old meter final read reconciles with new meter first read | Not run
TC-044 | Integration | MDMS/VEE | Outage-aware zero consumption | Inject zero consumption during a recorded outage | Treated as outage, not a validation failure | Not run
TC-045 | Integration | Billing | Meter-to-bill end to end | Run full billing cycle for pilot accounts | Bills correct against independent calculation | Not run
TC-046 | Integration | Billing | Billing determinants before cut-off | Monitor delivery timing | Delivered before cut-off; exceptions reported | Not run
TC-047 | Integration | Billing | Account events | Move-in, move-out, meter exchange, tariff change | Handled correctly in CIS and MDMS | Not run
TC-048 | Integration | OMS/GIS | Outage and restoration events | Simulate outages | Events reach OMS; restoration verified by ping | Not run
TC-049 | Integration | OMS/GIS | Transformer aggregation | Compare meter mapping with GIS | Aggregation matches network model | Not run
TC-050 | Integration | Consumer | CMDC and usage access | Consumer retrieves own data | Correct data; only own account visible | Not run
TC-051 | Integration | Data | Data export | Export all data types | Documented, non-proprietary format; complete | Not run
TC-052 | Security | Security | Vulnerability assessment | Independent scan of HES, MDMS, network, APIs | No open Critical; High only within deadline with compensating control (P6) | Not run
TC-053 | Security | Security | Penetration test | Independent test, including remote access and APIs | No open Critical; High only within deadline with compensating control (P6) | Not run
TC-054 | Security | Security | MFA and role-based access | Attempt privileged access without MFA; test roles | Denied; roles enforced | Not run
TC-055 | Security | Security | Network segmentation | Test paths between AMI, IT, and OT zones | Only approved flows possible | Not run
TC-056 | Security | Security | Logging and alerting | Generate security events | Logged centrally; alerts reach responders | Not run
TC-057 | Security | Security | Backup and restore | Restore HES/MDMS from backup | Restored within specified time; data complete | Not run
TC-058 | Security | Security | Incident response exercise | Tabletop exercise including regulatory notification | Plan executed; gaps recorded | Not run
TC-059 | Performance | Systems | Full-deployment volume | Load test at projected full volume plus growth | Processing within billing window | Not run
TC-060 | Performance | Systems | Report and dashboard response | Run standard reports at volume | Within specified response time | Not run
TC-061 | UAT | Users | Consumer services inquiry handling | Frontliners handle scripted scenarios | Resolved using system data | Not run
TC-062 | UAT | Users | Billing exception processing | Billing staff clear exception queue | Cleared per procedure | Not run
TC-063 | UAT | Users | Field installation and commissioning | Technicians install and commission | Completed per procedure, safely | Not run
TC-064 | UAT | Users | Loss analysis | Analyst runs transformer balancing report | Report correct; investigation list produced | Not run
TC-065 | Pilot | Evidence | Register-read reconciliation | Physical reads vs system values each cycle | Meets P1 threshold; all mismatches root-caused | Not run
TC-066 | Pilot | Evidence | Comparison-area analysis | Compare pilot and comparison areas over same period | Method and results documented | Not run
TC-067 | Integration | HES | Disconnection window reconfiguration | Change permitted days, hours, notice period, and holiday calendar as parameters | New windows enforced without software change | Not run
TC-068 | Integration | HES | Wrapped key import and key replacement after commissioning | Import manufacturing keys in wrapped form; replace with utility keys | Keys never exposed in clear; old keys rejected | Not run
TC-069 | Security | Security | Private APN / VPN for cellular meters | Attempt to reach meters from the public internet | No route; traffic only through private APN or VPN | Not run
TC-070 | Security | Security | Supply-chain evidence | Review SBOM, disclosure process, signing-key controls, vendor jump-host access | Meets Annex E.6 | Not run
TC-071 | Security | Security | Tenant isolation and platform-wide disconnect cap (shared platforms) | Attempt cross-tenant access; attempt disconnects above the platform cap | No cross-tenant access; cap enforced | Not run

## P6 Defect Log
P6: Defects and Security Findings
Stages P, R, and E2 · Protocol Sections 8, 16.1. Functional defects and security findings use separate severity scales. Security findings carry remediation deadlines; the gate checks below apply the Section 16.1 rule.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Scale | Severity | Definition |  |  |  |  | Remediation deadline (days) |  |  | Gate checks | Count / result |  |  |  |  | Functional scale (lookup) | Security scale (lookup)
Functional | Critical | Safety risk, wrong bills at scale, or loss of core function; no workaround |  |  |  |  | Critical | 15 |  | Open functional Critical/Major | 0 |  |  |  |  | Critical | Critical
Functional | Major | Core function impaired; workaround not sustainable |  |  |  |  | High | 30 |  | Open security Critical | 0 |  |  |  |  | Major | High
Functional | Minor | Non-core function impaired, or acceptable workaround |  |  |  |  | Medium | 90 |  | Open security High past deadline or without compensating control | 0 |  |  |  |  | Minor | Medium
Functional | Cosmetic | No functional impact |  |  |  |  | As-of date | 2026-09-22 |  | Critical or High past deadline (Gate 5 cohort check) | 0 |  |  |  |  | Cosmetic | Low
Security | Critical / High / Medium / Low | Rated with a recognized scoring method such as CVSS; remediation deadlines at right | [7 empty] | Gate 3 / Gate 4 check | No entries: confirm P5 tests have been run
[10 empty] | Gate 5 cohort security check | MET
Rows whose severity is outside the Type’s scale (must be 0)
“Accepted risk” counts as open. A Critical finding cannot be accepted as a risk at Gates 3–5; a High finding may remain open at Gates 3 and 4 only within its deadline, with an approved compensating control, and listed in the decision paper (Protocol 16.1).
For systems in service, a new Critical finding needs an approved compensating control within 72 hours, or the affected function (e.g., remote disconnection, firmware distribution) is suspended.
ID | Date raised | Test ID | Type | Description | Severity | Root cause | Corrective action | Owner | Target date (functional) | Security remediation deadline | Compensating control approved (Y/N) | Status | Retest result | Date closed | Deadline status
EXAMPLE D-001 |  | TC-023 | Functional | On-demand reads exceed specified latency in one feeder area | Major | Collector placement leaves weak links | Add repeater; re-survey | Vendor / TWG |  |  |  | Open

## P7 Analysis & Amendments
P7: Pilot Analysis Plan and Amendment Log
Stages M, P, E · Protocol Section 8.6 and Annex C.2 (applies SPIRIT 2025 principles). Complete the analysis plan before Gate 2; log every later change.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Analysis plan item | Entry
KPI calculation method and data source (reference P1 row for each KPI)
Measurement period (start and end dates)
Records excluded and reasons, limited to Protocol 8.6 and 21 (meters not commissioned; accounts disconnected all period; days in a declared calamity area or confirmed widespread outage; hours outside supply in off-grid areas)
Handling of missing data
Comparison-area method (separating AMI effects from seasonal and other effects)
How clustering (by area or concentrator) is handled
Technical-loss estimation method for the loss KPI (Protocol 21.3)
Pass rule: threshold, non-inferiority margin, one-sided 95% bound, and handling of inconclusive results (Protocol 8.6)
Census strata, low-volume segments, and any pooled sector evidence (source, n, comparability confirmation)
Who calculates results
Who independently verifies results
Consumer representatives consulted (who, when, what changed as a result)
How results will be shared with the Board and members
Plan approved by and date
Amendment log
# | Date | Section or KPI changed | Change | Reason | Made before or after results known? | Approved by | Date approved
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Changes made after results were known | 0
Any change made after results are known must be flagged in the Pilot Evaluation Report and the Gate 4 decision paper.

## W1 Risk Register
W1: Program Risk Register
All stages · Protocol Sections 5 and 12. Score likelihood and impact 1–5. Starting risks are common AMI risks; the utility must assess, add, and remove risks for its own situation.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Score | Likelihood | Impact |  | Rating rule
1 | Rare | Negligible |  | High: score ≥ 15 · Medium: 8–14 · Low: ≤ 7 (score = likelihood × impact)
2 | Unlikely | Minor
3 | Possible | Moderate |  | High risks open | 0
4 | Likely | Major |  | Unassessed risks | 26
5 | Almost certain | Severe
ID | Stage | Category | Risk (cause → event → consequence) | Likelihood | Impact | Score | Rating | Owner | Mitigation | Contingency | Due | Status | Last reviewed
RK-01 | M | Technical | Communication coverage in terrain, vegetation, or islands is below design, reducing read success
RK-02 | R | Technical | Typhoon damage or prolonged power loss disables collectors or concentrators
RK-03 | P | Integration | CIS/billing integration is late or unstable, delaying pilot billing or causing bill errors
RK-04 | A | Data | Poor meter-to-transformer mapping prevents energy balancing and undermines loss-reduction benefits
RK-05 | P | Commercial | Vendor delivery delay or foreign-exchange movement raises cost or delays schedule
RK-06 | M | Commercial | Proprietary interfaces or data formats create vendor lock-in
RK-07 | P | Consumer | Misinformation (e.g., “smart meters raise bills”) leads to resistance or complaints
RK-08 | P | Consumer | First AMI bills differ sharply from previously estimated bills, triggering disputes
RK-09 | R | Consumer | Remote disconnection executed on the wrong account or outside permitted rules
RK-10 | P | Cybersecurity | Compromise of HES or privileged accounts enables mass disconnection or data theft
RK-11 | P | Privacy | Personal data breach or unlawful data sharing
RK-12 | P | Security | Installer impersonation scams target consumers during rollout
RK-13 | A | Organization | Insufficient skilled staff or turnover of key personnel
RK-14 | R | Organization | Meter readers’ role change is not managed, causing labor relations issues
RK-15 | E1 | Regulatory | Regulatory approval is delayed or new ERC guidelines change requirements
RK-16 | E1 | Regulatory | Changes to system loss caps or pass-through treatment alter the business case
RK-17 | E1 | Regulatory | Write-off of undepreciated legacy meters is not recoverable
RK-18 | E2 | Technical | Carrier network shutdown or coverage change affects cellular-connected meters
RK-19 | R | Technical | Firmware defect disables meters or communication during a campaign
RK-20 | R | Safety | Installation safety incident
RK-21 | R | Operations | Theft or vandalism of meters, collectors, or batteries
RK-22 | E2 | Benefits | Loss analytics are produced but not acted on by field enforcement, so benefits are not realized
RK-23 | R | Legal | Theft cases fail because RA 7832 witness and evidence requirements were not met
RK-24 | M | Data | Master data errors (multipliers, tariff, transformer ID) cause wrong AMI bills
RK-25 | R | Logistics | Meters lost, stolen, or unaccounted for between warehouse and installation
RK-26 | A | Governance | Perceived conflict of interest where the advisor also offers solutions
RK-27
RK-28
RK-29
RK-30
RK-31
RK-32
RK-33
RK-34
RK-35
RK-36
RK-37
RK-38
RK-39
RK-40
RK-41

## W1 Gate Log
W1: Gate and Decision Log
All stages · Protocol Sections 5.1, 5.4 and Annex B. A decision that is not recorded has not been made.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Gate / decision | Date | Decision owner | Outcome | Conditions (owner, date) | Must criteria met (x of y) | Should criteria waived and reasons | Evidence references | Recorded by | Independent reviewer (name, organization) | Delivery confidence rating | Critical recommendations addressed? (Y/N) | Board resolution no. and date (Board decisions) | Allowed outcomes (Annex B.1, verbatim; lookup for column D, do not edit) | Gate
Gate 1: Proceed to Model | [12 empty] | Proceed | Gate 1: Proceed to Model
Gate 2: Pilot approval | [12 empty] | Proceed with conditions (Should criteria or gap-plan items only) | Gate 1: Proceed to Model
Gate 3: Technical acceptance | [12 empty] | Hold | Gate 1: Proceed to Model
Gate 4: Investment decision | [12 empty] | Approve as proposed | Gate 2: Pilot approval
Gate 5: Cohort checks (see R Rollout Cohorts) | [12 empty] | Approve with changes | Gate 2: Pilot approval
Change request after Gate 4 (Board-level) | [12 empty] | Return for further design | Gate 2: Pilot approval
Gate 5: Program handover | [12 empty] | Stop | Gate 2: Pilot approval
Annual review | [12 empty] | Accept | Gate 3: Technical acceptance
[13 empty] | Accept with corrective actions (Minor defects only) | Gate 3: Technical acceptance
[13 empty] | Retest after correction | Gate 3: Technical acceptance
[13 empty] | Reject | Gate 3: Technical acceptance
[13 empty] | Scale | Gate 4: Investment decision
[13 empty] | Scale with conditions | Gate 4: Investment decision
[13 empty] | Extend the pilot and correct | Gate 4: Investment decision
[13 empty] | Re-scope or re-procure | Gate 4: Investment decision
[13 empty] | Stop | Gate 4: Investment decision
[13 empty] | Continue | Gate 5: Cohort check
[13 empty] | Continue on watch (recheck next cycle) | Gate 5: Cohort check
[13 empty] | Pause and correct | Gate 5: Cohort check
[13 empty] | Re-plan remaining rollout | Gate 5: Cohort check
[13 empty] | Accept handover | Gate 5: Program handover
[13 empty] | Accept with conditions | Gate 5: Program handover
[13 empty] | Defer | Gate 5: Program handover
Independent review is required before Gates 2 and 4 (Protocol Section 5.4). Use template T9 for the review report.
Allowed outcomes differ by gate (Protocol Annex B.1). Conditions are allowed only for Should criteria, gap-plan items, or Minor defects, each with an owner and a deadline (Protocol 5.1); at Gate 4, “Scale with conditions” may also set program conditions in the Board resolution.

## W1 Tailoring & Deviations
W1: Tailoring and Deviation Register
All stages · Protocol Section 2.5. Record every tailoring decision and deviation, approved before the gate it affects. Items in the minimum mandatory set cannot be tailored.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Minimum mandatory set: all five gates with written decisions · knockout items and minimum readiness scores · measured baseline · Pilot Evaluation Plan with Must-Pass KPIs fixed before procurement, judged by stratum · register-read reconciliation · consumer safeguards (Section 17) · DPO and PIA · no open Critical, and no High past deadline, security findings at acceptance · independent review at Gates 2 and 4 (three-level rating permitted at Gate 2 on the lean path) · advisor disclosures and independent specification review (Section 13.3).
ID | Type | Protocol reference | Description | Reason | Risk and mitigation | Gate affected | Affects minimum mandatory set? (Y/N) | Approved by | Date | Check
EXAMPLE TD-01 | Tailoring | 8.6 | Pilot precision ±2 points (≈280 meters per stratum) | Utility size and budget | Non-inferiority margin fixed at Gate 2; inconclusive results extended | Gate 2 | N | Steering Committee

## W1 Document Register
W1: Program Document Register
All stages · Protocol Section 5.1. A deliverable counts toward a gate only when its designated approver has approved it.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Doc ID | Title | Stage | Version | Status | Owner | Designated approver | Approval date | Location | Notes
A-1 | Readiness Assessment Report | A |  | Not started
A-2 | Operational Baseline Report | A |  | Not started
A-3 | Meter and Systems Inventory | A |  | Not started
A-4 | AMI Objectives Statement | A |  | Not started
A-5 | Gap Closure Plan | A |  | Not started
M-1 | Requirements Specification | M |  | Not started
M-2 | Communication Feasibility Report | M |  | Not started
M-3 | Solution Architecture | M |  | Not started
M-4 | Privacy Impact Assessment | M |  | Not started
M-5 | Preliminary Business Case | M |  | Not started
M-6 | Pilot Evaluation Plan | M |  | Not started
M-7 | Procurement Package | M |  | Not started
M-8 | Pilot Consumer Engagement Plan | M |  | Not started
M-9 | Data Migration and Cleansing Plan | M |  | Not started
P-1 | FAT and SAT Reports | P |  | Not started
P-2 | Installation Records | P |  | Not started
P-3 | Security Test Report | P |  | Not started
P-4 | Monthly Pilot Performance Reports | P |  | Not started
P-5 | Pilot Cost Record | P |  | Not started
P-6 | Technical Acceptance Recommendation | P |  | Not started
E-1 | Pilot Evaluation Report | E |  | Not started
E-2 | Final Business Case | E |  | Not started
E-3 | Rollout Strategy | E |  | Not started
E-4 | Regulatory Application Package | E |  | Not started
E-5 | Board Decision Paper | E |  | Not started
R-1 | Wave Plans | R |  | Not started
R-2 | Wave Completion Reports | R |  | Not started
R-3 | Benefits Realization Report | R |  | Not started
R-4 | Legacy Meter Disposition Record | R |  | Not started
R-5 | Operations Handover Package | R |  | Not started
T9 | Independent gate review reports | M / E1 |  | Not started
W-1 | Workforce Transition Plan | E1 |  | Not started
C-1 | Consumer consultation record | E1 |  | Not started
S-1 | Specification bias review | M |  | Not started
T10 | Advisor conflict-of-interest disclosures | All |  | Not started
T11 | AMPERE conformance statements | All |  | Not started

## W1 Change Log
W1: Change Log After Gate 4
Stage R · Protocol Section 10.7. The approval level is calculated from the Board thresholds below (Metro Power recommended defaults; the Board may set its own).
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Approved program budget (PHP)
Board threshold: cost increase (% of budget) | 10%
Board threshold: delay (months) | 6
Board threshold: change in meter count (±%) | 15%
Change ID | Date | Description | Cost impact (PHP) | % of budget | Delay (months) | Meter count change (%) | Technology, vendor, area, or consumer-terms change? (Y/N) | Approval level | Approved by | Decision date | Status | Cumulative cost impact (% of budget) | Cumulative meter count change (%)
CR-01
CR-02
CR-03
CR-04
CR-05
CR-06
CR-07
CR-08
CR-09
CR-10
CR-11
CR-12
CR-13
CR-14
CR-15
CR-16
CR-17
CR-18
CR-19
CR-20
CR-21
CR-22
CR-23
CR-24
CR-25

## W1 Stakeholder Plan
W1/W3: Stakeholder Communication Plan
All stages · Protocol Sections 12, 14.1 and 17. Includes barangay and LGU coordination before field work.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Stakeholder | Main interest or concern | What they need to know | Method | Frequency / timing | Owner | Next date | Status
Board of Directors | Investment value, risk, member impact | Gate papers; progress; benefits
General Manager and management team | Delivery, cost, operations | Program status; decisions needed
Employees, including meter readers | Job changes; training | Role changes; redeployment; training plan
Employee representatives | Labor impact | Consultation on role changes
Consumers in pilot and wave areas | Bills, privacy, safety, installation | Why, when, what changes, whom to contact
Member-consumer-owner associations | Fairness, cost, rates | Benefits, rate impact, safeguards
Barangay officials | Community order, access | Schedule, installer identification, contacts
Local government units | Permits, public information | Schedule; permits; public advisories
ERC | Compliance; approval evidence | Approach; pilot evidence; applications; reports
NEA (electric cooperatives) | EC technical and financial soundness | Plans; financing; results
DOE | Policy alignment; cybersecurity framework | Program status; cybersecurity reporting if applicable
NPC (as required) | Personal data protection | Breach notification; PIA on request
Large commercial and industrial customers | Accuracy, data, supply choice | Meter change schedule; data access
Net-metering customers | Export measurement, credits | Bidirectional meter changes
Vendors and integrators | Scope, acceptance | Requirements; test results; defects
Local media and radio | Public information | Accurate program information

## W2 Cyber & Privacy
W2: Cybersecurity and Privacy Controls (NIST CSF 2.0) | [9 empty] | Not achieved
All stages · Protocol Sections 16.1–16.4 and Annex E.6. Record each control’s current and target state (CSF Profile) and one current and target Tier for the AMI program. All controls must be in place for the pilot environment at Gate 3. Under a sector framework, report verified control outcomes; the Tier is for information. | [9 empty] | Partially
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them. | [9 empty] | Largely
Fully
AMI program CSF Tier, current (1 Partial, 2 Risk Informed, 3 Repeatable, 4 Adaptive) | [9 empty] | Not applicable
AMI program CSF Tier, target
# | Control | Protocol ref. | CSF 2.0 function | Current state | Target state | Gap | Evidence (independently verified?) | Owner | Due
1 | Cybersecurity lead named; AMI covered by security policy | 16.1 | Govern |  | Fully
2 | Cybersecurity risk management strategy and risk appetite for AMI approved | 16.4 | Govern |  | Fully
3 | Risk assessment completed and updated at each gate | 16.1 | Identify |  | Fully
4 | Asset inventory of meters, modules, concentrators, network equipment, servers, and software versions; reconciled each cohort | 16.1 | Identify |  | Fully
5 | Network segmentation between AMI, IT, and OT; no direct internet exposure of HES/MDMS | 16.1 | Protect |  | Fully
6 | Cellular meters on a private APN or VPN; no public addressing | 16.1 | Protect |  | Fully
7 | Multi-factor authentication for all privileged and remote access | 16.1 | Protect |  | Fully
8 | Role-based access; quarterly reviews; segregation of duties for disconnect and VEE edits | 16.1 | Protect |  | Fully
9 | Unique per-device credentials verified in testing | 16.1 | Protect |  | Fully
10 | Signed firmware and secure boot verified in testing | 16.1 | Protect |  | Fully
11 | Encryption in transit and at rest verified | 16.1 | Protect |  | Fully
12 | Keys generated and held under utility control in a dedicated HSM or utility-controlled partition | 16.1 | Protect |  | Fully
13 | Manufacturing keys transferred only in wrapped form and replaced with utility keys after commissioning; no supplier holds usable keys | 16.1 | Protect |  | Fully
14 | Rate limits, time-window blocking (configurable windows), and alerts on remote disconnect and firmware commands; platform-wide cap if shared | 16.1 / 17.2 | Protect |  | Fully
15 | Security awareness training for all AMI staff and contractors; role-based training for privileged users | 16.1 | Protect |  | Fully
16 | Physical tamper events logged and monitored | 16.1 | Detect |  | Fully
17 | Centralized security logging and alerting operational | 16.1 | Detect |  | Fully
18 | Independent vulnerability assessment and penetration test; findings remediated within deadlines (P6) | 16.1 | Identify |  | Fully
19 | Incident response plan tested, including NPC, DOE, and DICT/CERT-PH notification where applicable | 16.1 / 16.3 | Respond |  | Fully
20 | Backup and restore of HES and MDMS tested; recovery time known | 16.1 / 16.5 | Recover |  | Fully
21 | Disaster recovery objectives set and failover tested | 16.5 | Recover |  | Fully
22 | Vendor and cloud contracts include security requirements, audit rights, and incident notification | 16.1 | Govern |  | Fully
23 | Supply chain: SBOM, vulnerability disclosure, protected signing keys, vendor access via utility jump host, hosting disclosed | Annex E.6 | Govern |  | Fully
24 | Tenant isolation tested independently in the last 12 months (shared platforms only) | 27.1 | Protect |  | Fully
25 | Coverage under DOE DC2025-01-0001 and DICT issuances confirmed; reporting calendar set if applicable | 16.3 | Govern |  | Fully
26 | DPO designated and involved | 16.2 | Govern |  | Fully
27 | Privacy Impact Assessment completed and reviewed | 16.2 | Identify |  | Fully
28 | Privacy notice published for AMI data | 16.2 | Govern |  | Fully
29 | Processing agreements with every vendor, host, and shared-platform operator | 16.2 | Govern |  | Fully
30 | NPC registration (where required) and cross-border transfer safeguards confirmed | 16.2 | Govern |  | Fully
31 | Retention periods defined per data category; billing-related data kept ≥ 5 years | 16.2 | Protect |  | Fully
32 | Data-sharing agreements for any third-party access | 16.2 | Govern |  | Fully
33 | Breach procedure can notify NPC and affected individuals within 72 hours | 16.2 | Respond |  | Fully
| Controls below target |  |  | 0
| Controls not yet assessed |  |  | 33

## W3 Complaint Log
W3: AMI Complaint Log and Escalation
Stages P, R, E2 · Protocol Section 17.5. Default targets: ≥ 95% acknowledged within 24 hours; standard ≤ 5 and complex ≤ 15 working days; meter tests ≤ 10 working days. Regulatory standards prevail.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Service-level parameter | Service-level value |  | Escalation trigger | Escalate to |  | Summary for reporting (K2) | Reporting value | [14 empty] | Public holidays (enter dates)
Acknowledge within (calendar days) | 1 |  | Billing dispute above the utility-set amount threshold | Billing review committee |  | AMI accounts at period end
Standard complaint resolution (working days) | 5 |  | Same account complains again within 60 days | Management review |  | Complaints logged | 0
Complex complaint resolution (working days) | 15 |  | Possible security or privacy incident | Cybersecurity lead and DPO, immediately |  | Complaints per 1,000 AMI accounts
Status update to consumer for open cases (working days) | 3 |  | Several similar complaints on one transformer, firmware version, or area within a week | TWG, systematic defect review |  | Acknowledged within target
Meter test turnaround from request (working days) | 10 |  | Vulnerable or medically dependent consumer affected by disconnection | Consumer services supervisor, immediately |  | Average working days to resolve
Resolved cases | 0 |  | Complaint filed with a regulator or involving legal action | Regulatory and legal |  | Average meter-test turnaround (working days)
Resolved within target | [5 empty] | Disconnection-safeguard breaches | 0
Privacy: this log contains personal data. Limit access to consumer services staff; use account numbers, not names, in reports.
Ticket | Date received | Channel | Account no. | Category | Description | Transformer / firmware / area | Complex? (Y/N) | Date acknowledged | Date resolved | Working days to resolve | Target (days) | Within target? | Escalated to | Root cause | Resolution | Meter test requested (Y/N) | Test request date | Test result reported date | Test working days | Test within target? | Disconnection-safeguard breach? (Y/N, Protocol 21.5)
EXAMPLE C-0001 |  | Hotline | [account] | High bill | Consumer reports bill higher than usual after meter change | TX-[id] / FW [ver] | N | [6 empty] | First actual read after estimated bills | Explained with usage data; no error found
Formulas:
Working days to resolve = IF(AND(ISNUMBER([Service-level value]),ISNUMBER([Date resolved])),NETWORKDAYS([Service-level value],[Date resolved],Y6:Y40)-1,"")
Test working days = IF(AND(ISNUMBER([Test request date]),ISNUMBER([Test result reported date])),NETWORKDAYS([Test request date],[Test result reported date],Y6:Y40)-1,"")

## W3 Consumer Education
W3: Consumer Education and Engagement Plan
Stages M, P, R · Protocol Section 17. Use the local language and channels consumers actually use.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Material or activity | Purpose | Audience | Channel | Language(s) | Timing | Owner | Status
Pre-installation notice letter | Explain why, when, what to expect, whom to contact | Consumers in installation area | Printed, hand-delivered |  | Before installation |  | Not started
Installer identification guide | Help consumers verify genuine installers and avoid scams | Consumers in installation area | Printed; SMS; social media |  | Before installation |  | Not started
Barangay assembly briefing | Answer questions face to face | Community | Barangay assembly |  | Before installation |  | Not started
Frequently asked questions | Address common concerns (bills, safety, privacy) | General public | Website; printed; social media |  | Before and during |  | Not started
Frontliner script and training | Consistent answers from hotline and counter staff | Consumer services staff | Training session |  | Before installation |  | Not started
SMS advisories | Installation schedule and service interruption notice | Affected consumers | SMS |  | Day before |  | Not started
First AMI bill explanation insert | Explain differences from previously estimated bills | Consumers receiving first AMI bill | Bill insert |  | First AMI bill |  | Not started
Privacy notice for meter data | Explain data collected, purpose, retention, rights | All AMI consumers | Printed; website |  | Before installation |  | Not started
Usage data (CMDC) guide | How to access own usage data | All AMI consumers | Printed; video; SMS |  | After installation |  | Not started
Prepaid service guide | Top-up, warnings, arrears treatment | Prepaid consumers | Printed; counter |  | At enrollment |  | Not started
Vulnerable consumer outreach | Identify and support seniors, PWDs, medically dependent households | Vulnerable consumers | Home visit; barangay referral |  | Before installation |  | Not started
Local radio segment | Wide public information | General public | Radio |  | Before and during |  | Not started
Short explainer video | Show installation and benefits | General public | Social media |  | Before and during |  | Not started

## K Reporting Cadence
K: Reporting Cadence
Stages P, R, E2 · Protocol Sections 11.3, 16.3 and 21. Adjust frequencies to the utility's size; do not drop regulatory reports.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Report | Content | Frequency | Audience | Prepared by | Reviewed / approved by | Timing
Operations dashboard | Read success, exception queues, failed commands, network alarms | Daily | Operations team | AMI operations lead | n/a | Each working day
Pilot status | Progress, KPIs vs thresholds, issues, complaints | Weekly (pilot) | Program team; TWG | Program Manager | TWG lead
Technical performance | Communications, HES/MDMS availability, firmware, defects | Monthly | Engineering and IT | TWG | Steering Committee
Billing and VEE | Estimated-bill rate, edits, exceptions, reconciliation results | Monthly | Billing; Internal Audit | Billing lead | Steering Committee
Consumer and complaints | Volumes, categories, SLA performance, clusters | Monthly | Consumer services; management | Consumer services lead | Steering Committee
Cybersecurity and privacy | Incidents, findings, access reviews, privacy requests | Monthly | IT; DPO; management | Cybersecurity lead | GM
Benefits and financial | Benefits realized vs business case; costs vs budget | Quarterly | Management; Board | Finance | GM
Steering Committee pack | All of the above plus risks and decisions required | Quarterly (monthly during pilot) | Steering Committee | Program Manager | Steering Committee chair
Board annual review | Protocol Section 11.3 contents | Annual | Board of Directors | GM | Board
Regulatory reports (ERC, NEA) | As required by applicable rules and approvals | As required | ERC; NEA | Regulatory affairs | GM | Per regulatory calendar
DOE cybersecurity submissions (if covered) | Cybersecurity Assessment Framework results and Cyber Resilience Scorecard; quarterly cyber issue reports | Annual (due April 30) and quarterly | DOE | Cybersecurity lead | GM | Confirm current requirements
Independent gate review report | Delivery confidence rating, findings, and recommendations (template T9) | Before Gates 2 and 4; optional at other gates | Decision owner; Steering Committee | Independent reviewer | n/a | Before the gate meeting
Prepaid self-disconnection | Share of prepaid consumers losing supply when credit runs out; duration; low-income breakdown | Every Steering Committee meeting | Steering Committee | Consumer services lead | GM
Consumer meter test results | Turnaround against target; results by outcome | Monthly | Consumer services; management | Metering lead | Steering Committee
Personal data breach notification | Notification to NPC and affected individuals | Event-driven | NPC; affected consumers | DPO | GM | Within 72 hours of knowledge

## K2 Sector Submission
K2: Sector Submission (Annex H dataset)
Used when the utility’s program is under a sector framework (Protocol Part III). Submit quarterly from Gate 2 until handover, then annually. Aggregated figures only; no personal data. The General Manager or delegate certifies each submission.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Data item | Source in this Toolkit | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Period 7 | Period 8
Utility
Period (e.g., 2026-Q4)
Peer group | Assigned by Adopting Body
AMPERE version followed | T11 conformance statement
Current stage | W1 Gate Log
Connections served
Last gate and outcome | W1 Gate Log
Last gate decision date | W1 Gate Log
Next gate and planned date | W1 Gate Log / P4
Lowest readiness category score (latest) | A1 Readiness Scoring
Lowest readiness category (category concerned) | A1 Readiness Scoring
Baseline system loss rate | A2 Baseline KPIs
Baseline estimated-bill rate | A2 Baseline KPIs
Baseline billing accuracy | A2 Baseline KPIs
Baseline billing-read availability | A2 Baseline KPIs
Baseline complaints per 1,000 accounts | A2 Baseline KPIs
AMI meters installed (cumulative) | R Rollout Cohorts
AMI meters commissioned (cumulative) | R Rollout Cohorts
Planned meters to date (approved plan)
Daily read success rate | P1 / operations
HES and MDMS availability
Remote command success
Billing accuracy (bills ≥90 days old) | P1 / billing
Estimated-bill rate | P1 / billing
Complaints per 1,000 AMI accounts | W3 Complaint Log summary
Average resolution time (working days) | W3 Complaint Log summary
Meter-test turnaround (working days) | W3 Complaint Log summary
Disconnection-safeguard breaches | W3 Complaint Log summary and HES disconnection review
Prepaid self-disconnection rate
Unresolved security findings | P6 (gate checks)
Security incidents in period
Personal data breaches notified
Outage event capture | Operations / OMS
Post-calamity recovery (if a calamity occurred) | Operations
Capital cost to date (PHP) | P3 / finance
Approved capital budget (PHP)
Operating cost to date (PHP) | Finance
Approved operating budget to date (PHP) | Finance
Benefits realized to date (PHP) | R Benefits Tracker
Benefits in approved business case to date (PHP)
Cohorts in pause or on watch | R Rollout Cohorts
Open gate conditions | W1 Gate Log
Approved tailoring decisions (count) | W1 Tailoring & Deviations
Open deviations (count) | W1 Tailoring & Deviations
Latest independent review rating | W1 Gate Log
Independent review rating at Gate 2 | W1 Gate Log
Independent review rating at Gate 4 | W1 Gate Log
Certified by (name, title, date)

## R Rollout Cohorts
R: Rollout Cohort Checks and Pause Triggers
Stage R · Protocol Sections 10.6, 10.9 and Gate 5. Each cohort is checked at its first full billing cycle. Installation continues while checks pass; any PAUSE stops new installations until the Steering Committee decides.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Maximum audit defect rate (Critical/Major ÷ audited) | 2%
Maximum complaints ratio vs pre-installation baseline | 2
Cohort | Area | Installation month | Meters installed | Commissioned | % commissioned | Installations audited | Audit Critical/Major defects | Audit defect rate | First-time-right % | Must-Pass KPIs met at first full cycle (Y/N) | Critical/High security findings past deadline (P6) | Complaints ÷ baseline | Next-area consumer notice done (Y/N) | If on watch: KPIs met at recheck (Y/N) | Check
CH-01
CH-02
CH-03
CH-04
CH-05
CH-06
CH-07
CH-08
CH-09
CH-10
CH-11
CH-12
CH-13
CH-14
CH-15
CH-16
CH-17
CH-18
CH-19
CH-20
CH-21
CH-22
CH-23
CH-24
CH-25
CH-26
CH-27
CH-28
CH-29
CH-30
Total |  |  | 0 | 0 |  | 0 | 0
Cohorts in PAUSE or HOLD | [14 empty] | 0
Cohorts on WATCH | [14 empty] | 0
Other pause triggers (Protocol 10.6) are recorded in the W1 Gate Log: a serious safety incident, a security incident or a Critical finding without an approved compensating control within 72 hours (P6), a batch or firmware failure pattern (E2 Failure Tracking), or estimated bills or billing corrections above threshold in any cycle.

## R Meter Logistics
R: Meter Logistics: Receiving Inspection and Stock Reconciliation
Stages P and R · Protocol Section 10.10. Register every device by serial number; accept lots only after sampling; reconcile stock daily.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Lot no. | Date received | Supplier | Model | Firmware | Quantity | Sample size | Defects found | Acceptance number (max defects) | Decision | Inspected by
Sample size and acceptance number come from the acceptance-sampling plan in the supply contract (for example, the IEC 62058 series).
Stock reconciliation
Date | Location | Device type | Opening | Received | Issued to installers | Returned | Closing (calculated) | Physical count | Variance | Investigated by / remarks

## R Benefits Tracker
R: Benefits Realization Tracker
Stages R and E2 · Protocol Sections 10 and 19.3. Report quarterly. A benefit counts only if its baseline was measured and a named owner delivers it.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Benefit | Business case annual value (PHP) | Baseline metric (from A2) | Current metric | Measured annualized value (PHP) | % of business case | Owner | Evidence | Last updated
Non-technical loss reduction
Meter-reading cost avoided
Field visits avoided
Billing error and dispute reduction
Collection improvement
Outage and operational savings
Asset and planning value
Total | 0 |  |  | 0

## E2 Failure Tracking
E2: Failure Rates and Warranty Tracking
Stages R and E2 · Protocol Section 20.3. Track annualized failure rate by model, batch, and firmware; invoke the serial-failure clause when a batch exceeds the contractual rate.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Model | Batch / lot | Firmware | Installed base (12-month average) | Failures in last 12 months | Annualized failure rate | Contractual or warranty rate | Flag | Warranty claims filed | Claims accepted | Root cause | Action
In-service accuracy sampling (Protocol 20.3)
Lot / batch | Model | Test date | Meters tested | Outside accuracy class | Allowed (sampling plan) | Result | Tested by | Remarks

## Regulatory Register
Regulatory Register
All stages · Protocol Section 14. Dated register: references current as of September 2026 and cited as amended or superseded. Confirm the issuance number and current text of each before relying on it.
Legend: yellow cells with blue text = enter data · white/grey cells = labels or formulas (do not overwrite) · rows marked EXAMPLE show the expected format; delete or overwrite them.
Instrument | Issuer | Relevance to AMI | Confirmed current on | Confirmed by | Owner | Next review | Notes
Amended Rules to Govern the Implementation of AMI (approved November 2025) and supplemental guidelines | ERC | Primary AMI rules; CMDC; approval route; technical, cybersecurity, and privacy requirements. Cite the resolution number from the issued text; track supplemental guidelines.
Resolution No. 16, Series of 2017: Type approval of smart meters | ERC | Type approval; IEC 62052/62053 or ANSI C12 certificates; five-year revalidation
Magna Carta for Residential Electricity Consumers, as amended, and any revised consumer charter | ERC | Disconnection notice and timing rules (at the time of writing: 48-hour written notice; no disconnection after 3:00 p.m. on weekdays, or on weekends and holidays). Amendments were under review in 2025–2026: confirm current text and update HES disconnection windows
ERC rules on meter testing, calibration, and sealing | ERC | Testing and sealing before installation; consumer-requested tests; confirm current procedures
Resolution No. 15, Series of 2009: Prepaid Retail Electric Service | ERC | Prepaid service rules; confirm amendments
Resolution No. 15, Series of 2025: Amended Net-Metering Rules | ERC | Bidirectional metering; credits; interconnection timelines
CAPEX approval rules and rate methodology applicable to the utility | ERC | Approval route and cost recovery
RA 7832 (Anti-Pilferage of Electricity Act), implementing rules, and ERC system loss rules | Congress / ERC | Theft enforcement: witnessed discovery, evidence, differential billing; system loss caps (under policy review in 2026)
RA 9513 (Renewable Energy Act of 2008) | Congress | Legal basis of net metering
Rules on Electronic Evidence | Supreme Court | Use of AMI data as evidence; confirm with counsel
Philippine Distribution Code (current edition) | ERC | Technical standards; reliability indices; metering
RA 9136 (EPIRA) and implementing rules | Congress / DOE | Distribution service framework; ERC authority
RA 10531 (NEA Reform Act) and NEA issuances | Congress / NEA | EC supervision; financing and technical oversight; EC procurement guidelines
RA 11039 (Electric Cooperatives Emergency and Resiliency Fund Act) | Congress / DOE / NEA | Post-calamity restoration funding for ECs; confirm AMI eligibility
RA 11646 (Microgrid Systems Act) and missionary electrification rules | Congress / DOE / ERC | Off-grid and missionary areas; cost recovery
RA 12009 (New Government Procurement Act) and other procurement rules applicable to the utility | Congress / GPPB | Confirm with counsel which procurement rules apply
RA 11032 (Ease of Doing Business Act) | Congress / ARTA | Processing times where an Adopting Body is a government agency
RA 10173 (Data Privacy Act), implementing rules, and NPC circulars | Congress / NPC | Lawful processing; DPO; processing agreements; registration where required; cross-border transfers; breach notification within 72 hours
RA 10844 (DICT Act) and DICT issuances on critical information infrastructure and incident reporting (CERT-PH) | Congress / DICT | CII protection; national incident reporting; confirm current requirements
RA 10535 (Philippine Standard Time Act) | Congress / PAGASA | Time source traceability for AMI
Labor Code of the Philippines and DOLE rules | Congress / DOLE | Workforce transition: consultation, redeployment, separation
Department Circular No. DC2025-01-0001: Energy Sector Cybersecurity and Cyber Resilience Framework | DOE | Annual CAF and CRS (April 30); VAPT; quarterly reports; CERT; confirm coverage
Executive Order No. 58: National Cybersecurity Plan 2023–2028 | Office of the President / DICT | National cybersecurity direction
RA 10175 (Cybercrime Prevention Act) | Congress | Cyber offenses and reporting
Radio equipment authorization and frequency rules | NTC | RF and cellular modules and network equipment
Retail Competition and Open Access rules (as amended 2025) | ERC | Interval data and data-sharing for contestable customers
RA 11058 (Occupational Safety and Health Standards) and DOLE rules | Congress / DOLE | Installation safety